## Project_Overview
Project Name | Project Manager | Start Date | Target Go-Live | Budget | Actual Cost | Status | Health Score
Hybrid Project Management System | John Smith | 2024-01-15 | 2024-06-30 | 150000 | 125000 | In Progress | Good

## WBS_TaskPlan
WBS ID | Task Name | Owner | Planned Start | Planned End | Planned Days | Actual Start | Actual End | Actual Days | % Complete | Status (RAG) | Dependencies
T001 | Project Initiation | Project Manager | 2025-10-12 | 2025-10-17 | 5 | 2025-10-12 | 2025-10-19 | 7 | 100 | Green
T002 | Requirements Gathering | Business Analyst | 2025-10-14 | 2025-10-24 | 10 | 2025-10-14 | 2025-10-26 | 12 | 100 | Green | T001
T003 | System Design | Solution Architect | 2025-10-16 | 2025-10-31 | 15 | 2025-10-16 | 2025-10-30 | 14 | 100 | Green | T002
T004 | Database Design | Database Architect | 2025-10-18 | 2025-10-26 | 8 | 2025-10-18 | 2025-10-28 | 10 | 100 | Green | T003
T005 | Frontend Development | Frontend Developer | 2025-10-20 | 2025-11-09 | 20 | 2025-10-20 | 2025-11-09 | 20 | 100 | Green | T004
T006 | Backend Development | Backend Developer | 2025-10-22 | 2025-11-16 | 25 | 2025-10-22 |  |  | 41 | Red | T005
T007 | API Development | Backend Developer | 2025-10-24 | 2025-11-05 | 12 | 2025-10-24 |  |  | 77 | Green | T006
T008 | Integration Testing | QA Engineer | 2025-10-26 | 2025-11-03 | 8 | 2025-10-26 |  |  | 36 | Red | T007
T009 | User Acceptance Testing | QA Engineer | 2025-10-28 | 2025-11-07 | 10 |  |  |  | 0 | Red | T008
T010 | Deployment | DevOps Engineer | 2025-10-30 | 2025-11-02 | 3 |  |  |  | 0 | Red | T009
T011 | Training | Project Manager | 2025-11-01 | 2025-11-06 | 5 |  |  |  | 0 | Red | T010
T012 | Go-Live Support | Support Team | 2025-11-03 | 2025-11-10 | 7 |  |  |  | 0 | Red | T011

## Risk_Issue_Log
ID | Type (Risk/Issue) | Description | Probability (0-1) | Impact (1-5) | Score (P*I) | Owner | Mitigation/Action | Status
RISK-001 | Risk | Key developer may leave during critical phase | 0.3 | 4 | 1.2 | Project Manager | Cross-train team members, prepare backup resources | Open
RISK-002 | Risk | Third-party API rate limits may impact performance | 0.4 | 3 | 1.2 | Technical Lead | Implement caching and request optimization | In Progress
ISSUE-003 | Issue | Database performance degradation in test environment | 1 | 2 | 2 | Database Administrator | Optimize queries and add indexes | Closed
RISK-004 | Risk | Budget constraints may limit scope | 0.2 | 5 | 1 | Project Manager | Prioritize features, prepare scope reduction plan | Open
ISSUE-005 | Issue | User interface not meeting accessibility requirements | 1 | 3 | 3 | Frontend Developer | Redesign components for WCAG compliance | In Progress

## Sprint_Planner
Sprint | User Story | Estimate (pts) | Status | Actual Effort (hrs) | Owner
Sprint 1 | User Authentication Sprint 1 | 5 | Done | 10 | Developer C
Sprint 1 | Dashboard Features Sprint 1 | 8 | Done | 11 | Developer A
Sprint 1 | API Integration Sprint 1 | 3 | Done | 7 | QA Engineer
Sprint 1 | User Management Sprint 1 | 5 | Done | 5 | Developer C
Sprint 1 | Reporting Features Sprint 1 | 5 | In Progress |  | Developer A
Sprint 1 | Performance Optimization Sprint 1 | 3 | To Do |  | Developer B
Sprint 1 | Testing Sprint 1 | 2 | To Do |  | Developer B
Sprint 2 | User Authentication Sprint 2 | 5 | Done | 9 | QA Engineer
Sprint 2 | Dashboard Features Sprint 2 | 8 | Done | 4 | Developer A
Sprint 2 | API Integration Sprint 2 | 3 | Done | 10 | Developer C
Sprint 2 | User Management Sprint 2 | 5 | Done | 6 | Developer C
Sprint 2 | Reporting Features Sprint 2 | 5 | In Progress |  | QA Engineer
Sprint 2 | Performance Optimization Sprint 2 | 3 | To Do |  | Developer C
Sprint 2 | Testing Sprint 2 | 2 | To Do |  | QA Engineer
Sprint 3 | User Authentication Sprint 3 | 5 | Done | 11 | Developer C
Sprint 3 | Dashboard Features Sprint 3 | 8 | Done | 9 | QA Engineer
Sprint 3 | API Integration Sprint 3 | 3 | Done | 9 | Developer B
Sprint 3 | User Management Sprint 3 | 5 | Done | 7 | Developer C
Sprint 3 | Reporting Features Sprint 3 | 5 | In Progress |  | Developer C
Sprint 3 | Performance Optimization Sprint 3 | 3 | To Do |  | Developer A
Sprint 3 | Testing Sprint 3 | 2 | To Do |  | Developer B
Sprint 4 | User Authentication Sprint 4 | 5 | Done | 11 | Developer A
Sprint 4 | Dashboard Features Sprint 4 | 8 | Done | 11 | Developer B
Sprint 4 | API Integration Sprint 4 | 3 | Done | 6 | Developer A
Sprint 4 | User Management Sprint 4 | 5 | Done | 11 | QA Engineer
Sprint 4 | Reporting Features Sprint 4 | 5 | In Progress |  | Developer A
Sprint 4 | Performance Optimization Sprint 4 | 3 | To Do |  | Developer A
Sprint 4 | Testing Sprint 4 | 2 | To Do |  | Developer C
Sprint 5 | User Authentication Sprint 5 | 5 | Done | 6 | Developer C
Sprint 5 | Dashboard Features Sprint 5 | 8 | Done | 5 | QA Engineer
Sprint 5 | API Integration Sprint 5 | 3 | Done | 5 | Developer A
Sprint 5 | User Management Sprint 5 | 5 | Done | 5 | Developer B
Sprint 5 | Reporting Features Sprint 5 | 5 | In Progress |  | QA Engineer
Sprint 5 | Performance Optimization Sprint 5 | 3 | To Do |  | Developer B
Sprint 5 | Testing Sprint 5 | 2 | To Do |  | Developer C

## Weekly_Updates
Week Start | Tickets Opened | Tickets Resolved | NPS | CSAT | Notes

## KPI_Dashboard
Metric | Value | Trend